## GOBYS (hidden)
GO-BY'S
DWG | HRS
PP | 20
PFD | 20
PID | 40
GA-PLAN | 40
GA-SECT | 20
GA-ISO | 10
ISOMETRIC | 3.5

## MATRIX
Client:
Project:
Number:
Date:
|  |  | Rev: | Rev 0
Project Description / Scope
Brief Project Description here
DELIVERABLE & RESPONSIBILITY MATRIX
DELIVERABLE | Client | Bluestar | Required | COMMENTS
PROJECT MANAGEMENT
Quality Process FlowChart |  | X | YES
DBM |  | X | YES | To be approved by Client
AFE Estimate |  | X | YES | To be approved by Client
Schedule |  | X | YES | To be approved by Client
Cost Reporting & Forecasts |  | X | YES | Procurement Log to be updated on a regular basis including engineering cost
Process Safety Management (PSM) | X | X | YES | to differentiate between critical and non-critical process safety requirements and build this into the engineering and procurement processes. Include all relevant disciplines such as Structural, Rotating Equipment, I&C, and Electrical.
ENGINEERING AND DESIGN
Process Simulation |  | X | YES | Hysys
Pipeline Model (Hydraulics and pipe sizing) |  | X | YES
Stress Calculations and Analysis |  | X | YES
Environmental Studies | X |  | YES | If required (TBC) soil, EFR, COP, etc
Geotechnical Studies |  | X | YES
HDD Crossing Design |  | X | YES | For major water crossings
Cathodic Protection (CP) Design |  | X | YES
Hydrotest Test Pressure Plan |  | X | YES | Bluestar to review and approve Contractor Pressure Testing Procedure if required
Welding Procedure |  | X | YES | Bluestar to review and approve Contractor Pressure Welding Procedure if required
REGULATORY
Land Acquisition | X |  | YES
Participant Involvement Program and Crossing Agreements | X |  | YES
Regulatory Permits & Approvals |  |  |  | Please check requirements specific for each province (this list is referring Alberta requirements)
D56 Notification Letter | X | X | YES | By Client with Bluestar support
AER License Application and Audit Book |  | X | YES
DDS Notifications (Construction and Testing) |  | X | YES
ABSA Application |  | X | YES
Development and Building Permits |  | X | YES
Aeronautical Clearance Form (Flares, Towers, etc) |  | X | YES
AUC Utility Power Applications |  | X | YES
AENV Code of Practice or Permits |  | X | YES
Noise Impact Assessment (NIA) |  | X | YES
Dispersion Modelling (NOx/Sox) |  | X | YES
D60 Gas Conservation (Decision Tree) | X | X | YES
PROCUREMENT
Procurement and Expediting Log |  | X | YES | To be updated on a regular basis and to be discussed during weekly meetings as required
Requisition for Quotation (RFQ/RFP) |  | X | YES | For Materials and Services
Technical Bid Evaluation |  | X | YES
Commercial Bid Evaluation |  | X | YES
Purchase Requisitions (PR) |  | X | YES | Client Project Manager to approve and sign PO before issuing to Vendor
Purchase Order (PO) |  | X | YES | Client Project Manager to approve and sign PO before issuing to Vendor
Vendor Document Review |  | X | YES
Material Expediting |  | X | YES
Data Manuals |  | X | YES | IF REQUIRED
Survey / Existing Drawings
Lease / Wellpad Surveys | X |  | YES | by Survey Company
Topographic Map (lease elevations) | X |  | YES | by Survey Company
ROW and Crossing Surveys | X |  | YES | by Survey Company
HDD profiles | X |  | YES | by Survey Company
Existing Drawings (mechanical, electrical, etc) | X |  | YES
Mechanical / Piping
Drawing Index |  | X | YES
Plot Plan |  | X | YES
PFD |  | X | YES
P&ID |  | X | YES
General Arrangements |  | X | YES
ISO's |  | X | YES
3D Model |  | X | YES
Video |  | X | YES
Pipeline Route Map |  | X | YES
Pipeline Alignment Sheets |  | X | YES | Pipeline Route Maps will suffice
Line List |  | X | YES | If required
Bends List |  | X | YES
Bill of Materials (BOM) |  | X | YES
Equipment List |  | X | YES
Equipment Data Sheets |  | X | YES
Manual Valve List |  | X | YES
Specialty Items List |  | X | YES
Piping Stress Analysis |  | X | YES
Demolition Drawings |  | X | YES
As-Builts |  | X | YES | IF REQUIRED
Civil / Structural
Drawing Index |  | X | YES
Piling & Foundation drawings |  | X | YES
Structural Drawings |  | X | YES
Pipe Support Drawings |  | X | YES
Grade & Finished Grade drawings |  | X | YES
Road design & drawings |  | X | YES
As-Builts |  | X | YES
Electrical
Drawing Index |  | X | YES
Electrical Plot Plan / Cable Layout |  | X | YES
Area Classification |  | X | YES
Grounding Layout |  | X | YES
Control Panel Layout |  | X | YES
MCC Building Layout |  | X | YES
MCC Elevation Drawings |  | X | YES
Switchgear Elevation Drawings |  | X | YES
4160V Single Line Diagrams |  | X | YES
4160V Control Schematics |  | X | YES
480V Single Line Diagrams |  | X | YES
480V Control Schematics |  | X | YES
120V Control Schematics |  | X | YES
UPS Schematic |  | X | YES
Conduit/Cable Schedule |  | X | YES
Heat Trace Schedule |  | X | YES
Junction Box Details |  | X | YES
Electrical Data Sheets |  | X | YES
Electrical Installation Details |  | X | YES
Coordination / Short Circuit / Arc Flash Study |  | X | YES
Electrical Load / Sizing Calculations |  | X | YES
As-Builts |  | X | YES
Instrumentation & Control
Control Narrative |  | X | YES
Shutdown Key |  | X | YES
Instrument Sizing Calcs |  | X | YES
Instrument Data Sheets |  | X | YES
Instrument Index |  | X | YES
24VDC Distribution |  | X | YES
24V Control Schematics |  | X | YES
I/O Schematics |  | X | YES
Control System Architecture |  | X | YES
PROGRAMMING
HMI |  | X | YES
PLC |  | X | YES
OMNI |  | X | YES
SCADA |  | X | YES | If required for Leak Detection & Gas Meters
REVIEWS
Design / Process Review | X | X | YES
Model & Drawing Review including: | X | X | YES | 30%, 60% and 90%
Mechanical | X | X | YES
Electrical & Instrumentation | X | X | YES
Civil and Structural | X | X | YES
HAZOP/ What-if | X | X | YES
Deficiency List |  | X | YES
CONSTRUCTION/TURNOVER
Construction Package - Project Info |  | X | YES
Construction Package - Drawings |  | X | YES
Data Book |  | X | YES | Construction QC Quality to be provided by Mechanical Contractor
Notes: 1) The above list of engineering activities/deliverables is not meant to be exhaustive, but to clarify any areas of potential overlap 2) Any additional activities must be verified and approved by Client
APPROVAL
Client |  |  |  | Date
Bluestar Engineering Ltd. |  |  |  | Date

## Engineer
Project:
Number:
Client:
Date:
Rev:
PROJECT ENGINEERING - DETAILED ESTIMATE
Code | DESCRIPTION | Estimated Man-hours | Total | COMMENTS
PROJECT IFI - SCOPING & STARTUP |  |  |  | 1038
100 | Preliminary DBM | Hours | 122
| - Complete Project Initiation Form | 2
| - DBM Initiation | 80
| - Review and Mark up | 40
101 | Class 4 AFE Cost Estimate and Schedule | Hours | 130
| - Class 4 Estimate (± 50%-75%) | 60
| - Review and Mark up | 20
| - Project Schedule | 30
| - Internal Schedule Review / Mark up | 20
102 | Preliminary Calculations | Hours | 120
| - Equipment Selection - Sizing, data sheets | 80 |  | Main Pumps, Injection Pumps and Bullet
| - Equipment and Pipeline Recommendation | 40
103 | Simulation and Modeling | Hours | 40 |  | Preliminary DBM
| - Process Simulations | 0 |  |  | Class 3 AFE Cost Estimate
| - Piping Sizing | 20 |  |  | Preliminary Calculations
| - Calculations | 20 |  |  | Preliminary Hydraulics
104 | Preliminary plot plan/PFD/ Schematic | Hours | 60 |  | Preliminary PFD/ Schematic Creation
| -Initiate PFD/plot plan | 60 |  |  | Preliminary Procurement
Preliminary Regulatory
Preliminary Meeting
105 | Procurement - Long Lead Items | Hours | 280
| - Prepare RFQ | 80 |  | Main Pumps, Injection Pumps, Bullet, VFD
| - Issue documentation to vendor and liaison during the procurement | 60
| - Bid Evaluation & Clarifications | 100
| - Prepare Purchase Requisition/ Order | 40
106 | Preliminary Regulatory | Hours | 2
| - D56 Notification Letter | 0
| - Establish regulatory requirements for project | 2
107 | Preliminary Meetings | Hours | 160
| - Project Scoping Meeting/ Discussion /MoM | 80 |  | 4 people, 4hr/week/person for one month (includes phone discussions)
| Internal meetings - Brain storming | 80
108 | Document Control | Hours | 60
| - Meeting/ Discussion / Revise Pembina Procedures | 40
| - Document control numbers and templates | 20
109 | Site Visit | Hours | 64
| Site Visit | 64 |  | 4 people, 16 hrs
PROJECT IFR - REVIEW AND HAZOP |  |  |  | 1395
200 | IFR DBM Update | Hours | 60
| - Update DBM | 40
| - DBM Review | 20
201 | IFR Class 3 AFE Cost Estimate | Hours | 60
| - Update Class 3 Estimate (± 30%-50%) | 40
| - Estimate Internal Review/ Mark Up | 20
202 | Project Schedule Creation | Hours | 50
| - Update Project Schedule | 30
| - Internal Schedule Review / Mark up | 20
203 | Procurement | Hours | 400
| - Vendor Drawing Review and Approval | 120 |  | Main Pumps, Injection Pumps, Bullet, VFD
| - Prepare RFQ for next priority items | 80
| - Issue documentation to vendor and liaison during the procurement | 60
| - Bid Evaluation & Clarifications | 100
| - Prepare Purchase Requisition/ Order | 40
204 | IFR P&ID | Hours | 224
| - Project Site Visit | 48 |  | 3 people, 16hr per visit for 1 visit
| - Initiate IFI P&ID Drafting | 80
| - Internal IFR Review | 60
| - Client Drawings Review Meeting | 32 |  | 4 people, 8hr
| - Issue Drawings To Client | 4 |  | Document control
205 | IFR Model | Hours | 47
| - Initiate Drafting IFR | 20
| - Client Drawings Review Meeting | 16 |  | 4 people, 4 hours
| - Issue Drawings To Client | 2
| - Client Model Review Meeting | 8 |  | 4 people, 2hr
| - Issue Model To Client | 1
206 | HAZOP | Hours | 212
| - HAZOP Checklist Creation | 20
| - HAZOP Drawing Package Creation (IFH) | 20 |  | Document Control
| - HAZOP Document Creation | 60
| - HAZOP Meeting | 32 |  | 4 people, 8 hrs
| - HAZOP 3rd Party Services | 20
| - HAZOP Action list and follow up | 60
207 | Progress Meeting | Hours | 272
| - Weekly project Meeting/ MoM | 64 |  | 4 people, 2hr weekly for two months
| - Review Meeting | 64 |  | 2 people, 8hr per meeting for 4 meetings
| - Biweekly project Meeting with vendor | 96 |  | 2 people, 1hr weekly for 12 months
| - Shop visit to vendor facility | 48 |  | 2 people, 8hr per meeting for 3 visits
208 | Document Control | Hours | 70
| - QC of documents as per Pembina Document Control Procedures | 40
| - Transmittal & Distribution of Documents | 30
PROJECT REV IFB - CLIENT APPROVAL |  |  |  | 1647
300 | IFB DBM | Hours | 60
| - Updated DBM with HAZOP Comments | 40
| - DBM Review | 20
301 | IFB Class 2 AFE Cost Estimate | Hours | 60
| - Update Estimate - Class 2 (±10%-20%) | 40
| - Estimate Internal Review/ Mark Up | 20
302 | IFB Project Schedule | Hours | 50
| - Update Schedule with HAZOP Comments | 30
| - Internal Estimate Review/ Mark Ups | 20 |  |  | IFB DBM
IFB Class 2 AFE Cost Estimate
303 | IFB Procurement | Hours | 670 |  | IFB Project Schedule
| - Vendor Drawing Review and Approval | 60 |  | Next priority items (Flare, sump tank/pump, etc)
| - Prepare Mechanical construction Bid Doc | 60 |  |  | IFB Procurement
| - Prepare Bid Doc for Construction services (hydrovac, piling, civil, land locating, x ray, etc) | 60 |  |  | IFB Procurement
| - Prepare Electrical construction Bid Doc | 60 |  |  | IFB Procurement
| - Prepare Equipment RFQ | 60 |  |  | IFB P&ID
| - Prepare Materials RFQ | 40 |  |  | IFB Piping Design
| - Bid evaluation, Clarifications and Award contract | 200 |  | For materials, equipment and mech/electr construction | Electrical Engineering Package
| - Award contract Meetings | 50 |  | as project needs | Electrical Engineering Package
| - Issue Purchase Order/ Requisition | 80 |  |  | Stress Engineering Initiation
IFB Class 2 AFE Cost Estimate
304 | IFB P&ID | Hours | 136 |  | IFB Regulatory
| - Updated/ Review P&ID with HAZOP Comments | 80
| - Internal IFR Review | 20
| - Client Drawings Review Meeting | 32 |  | 4 people, 8hr
| - Issue Drawings To Client | 4 |  | Document control
305 | IFB Model | Hours | 40
| - Updated/ Review model with HAZOP Comments | 40
306 | IFB Piping Design | Hours | 60
| - Review IFB Piping Design | 40
| - Review ISO | 20
307 | IFB Structural Design | Hours | 40
| - Review IFB Structural Design | 40
308 | Electrical Engineering Package | Hours | 260
| - Create Scope of Work for Electrical team | 40
| - Electrical List, calculations, sizing | 40
| - Review IFA Electrical Drawings | 40
| - Prepare Control Narrative | 40
| - Prepare Shut Down Key | 60
| - Prepare/ Check Electrical Instrument Data | 40
309 | Stress Engineering Initiation | Hours | 45
| - Create SOW for Stress team | 30
| - Meet with Stress Team | 10
| - Review IFA Stress Recommendations | 5
310 | IFB Regulatory | Hours | 60
| - Energy Development Application & submission (AER, OGC, etc) | 10 |  | By Pembina, only support
| - Prepare ABSA Registration, or equivalent | 40
| - Other Regulatory Requirements As per project needs | 10 |  | Noise data
311 | Progress Meeting | Hours | 96
| - Weekly project Meeting/ MoM | 96 |  | 4 people, 2hr weekly for three months
312 | Document Control | Hours | 70
| - QC of documents as per Pembina Document Control Procedures | 40
| - Transmittal & Distribution of Documents | 30
PROJECT REV IFC - CONSTRUCTION PACKAGE |  |  |  | 606
400 | IFC DBM | Hours | 40
| - Finalize and Issue DBM | 40
401 | IFC Class 1 AFE Cost Estimate | Hours | 72
| - Class 1 Estimate (± 1%-10%) | 40
| - Cost Control | 32 |  | 2 people, 2hr weekly for two months
402 | IFC Project Schedule | Hours | 50
| - Finalize Project Schedule | 30
| - Track Project Progress | 20
403 | IFC Procurement | Hours | 128
| - PVF Procurement | 40
| - Review QA/QC packages | 40
| - Procurement Plan / Expedite | 48 |  | 2 people, 3hr weekly for two months
404 | IFC P&ID | Hours | 10
| - Review IFC P&ID | 10
405 | IFC Model | Hours | 10
| - Review IFC Model | 10
406 | IFC Structural Design | Hours | 10
| - Review IFC Structural Design | 10
407 | IFC Electrical Engineering Package | Hours | 60
| - Review IFC Electrical Drawings | 10
| - Issue Control Narrative | 20
| - Issue Shut Down Key | 30
408 | IFC Stress Engineering Initiation | Hours | 10
| - Review IFC Stress Design | 10
409 | IFC Sign Off | Hours | 20
| - Completed IFC package Sign off | 20
410 | Regulatory | Hours | 30
| - Submit ABSA registration, or equivalent | 30 |  | With follow up
411 | Progress Meeting | Hours | 96
| - Weekly project Meeting/ MoM | 96 |  | 4 people, 2hr weekly for three months
412 | Document Control | Hours | 70
| - QC of documents as per Pembina Document Control Procedures | 40
| - Transmittal & Distribution of Documents | 30
PROJECT CONSTRUCTION |  |  |  | 628
500 | Construction Kick off Meeting | Hours | 200
| - Prepare Construction Packages | 60
| - Prepare Drawing Binders | 60
| - Attend Construction Kick off Meeting | 48 |  | 2 people, 2-day travelling
| - Site visit to project site for start-up/as-building | 32 |  | 2 people, 16hr per visit for 1 visit
501 | Construction Support | Hours | 188
| - Construction Support | 64 |  | 2 people, 2hr weekly for 4months
| - Attend Meetings | 60 |  | as required
| - Cost Control | 64 |  | 2 people, 2hr weekly for 4months
502 | Data Book | Hours | 120
| - Prepare Data Books | 80
| - Review QC information from Vendors | 40
503 | Document Control | Hours | 120
| - QC of documents as per Pembina Document Control Procedures | 80
| - Transmittal & Distribution of Documents | 40
PROJECT COMPLETION |  |  |  | 100
600 | Turnover Package | Hours | 100
| - Complete Turnover Package | 60
| - Handover Turnover Package | 40
| Contingency | Hours | 0
| ENGINEERING HOURS |  | 5414 | Man-hours
| DRAFTING HOURS |  | 3100 | Man-hours (Next Page)
| TOTAL HOURS |  | 8514 | Man-hours
| TOTAL COST | 1170675

## Drafting
DRAFTING MANHOURS
Project:
Number:
Client:
Date:
Rev:
Project Description
Brief Project Description here | [6 empty] | Project Milestone Dates
Project Start :
IFR and 1st Model Review :
IFH and 2nd Model Review :
3rd Model Review :
IFB :
IFC :
Project End :
BWBS | PIPING ESTIMATE | [5 empty] | Bluestar Drafting Work Breakdown Structure |  |  | Actual | Left | %
Code | DESCRIPTION | HRS/ | QTY | HRS | COMMENTS |  | Code | DESCRIPTION | HRS | HRS | HRS
1ST DELIVERABLES | [6 empty] | 0 0 1 | Supervision | 223.024 |  |  | 0%
1 5 0 | COVER PAGE | 1 | 1 | 1 |  |  | 0 0 2 | Meetings | 140 |  |  | 0%
1 5 0 | DWG INDEX | 10 | 1 | 10 |  |  | 0 0 3 | Field Trip | 60 |  |  | 0%
[7 empty] | 0 2 0 | Checking PFD/P&ID/PLOT | 42 |  |  | 0%
1 0 0 | PLOT PLAN | 40 | 1 | 40 | Including Preliminary versions for discussion |  | 0 2 1 | Checking GA's | 90 |  |  | 0%
1 0 0 | KEY PLAN | 4 | 2 | 8 |  |  | 0 2 2 | Checking Iso's | 10 |  |  | 0%
[7 empty] | 0 3 0 | Checking Structural | 30 |  |  | 0%
1 5 0 | PFD (Existing) |  | 0 | 0 |  |  | 0 4 0 | Checking Civil | 20 |  |  | 0%
1 5 0 | PFD (New) | 40 | 1 | 40 | Including Preliminary versions for discussion |  | 0 5 0 | Checking Arch | 5 |  |  | 0%
[7 empty] | 1 0 0 | Plot plan/Key Plan | 48 |  |  | 0%
1 5 0 | P&ID (Demo) |  | 3 | 0 |  |  | 1 5 0 | PFD/P&ID | 271 |  |  | 0%
1 5 0 | P&ID (Existing) |  | 0 | 0 |  |  | 2 0 0 | 3D Model (Piping) | 300 |  |  | 0%
1 5 0 | P&ID (New) | 10 | 20 | 200 |  |  | 2 1 0 | 3D Model (Equipment) | 75 |  |  | 0%
1 5 0 | P&ID (As-Built) | 1 | 20 | 20 |  |  | 2 2 0 | Piping GA's/Sects/Isoviews | 200 |  |  | 0%
[7 empty] | 2 3 0 | Piping Isometrics | 50 |  |  | 0%
MODELLING | [6 empty] | 2 5 0 | Pipeline Route Maps | 0 |  |  | 0%
2 0 0 | Piping Modelling | 10 | 30 | 300 | 10 Hrs / PRM & GA |  | 3 0 0 | 3D Model (Structural) | 0 |  |  | 0%
2 1 0 | Equipment Modelling | 5 | 15 | 75 | 5 hrs / piece of Equipment |  | 3 2 0 | Struct GA's/Sects/Isoviews | 72 |  |  | 0%
[5 empty] | Pumps, bullet, sump / flare system, basket, etc |  | 4 0 0 | 3D Model (Civil) | 0 |  |  | 0%
2ND DELIVERABLES | [6 empty] | 4 2 0 | Civil GA's/Sects/Isoviews | 30 |  |  | 0%
2 2 0 | GA (Demo) |  | 0 | 0 |  |  | 5 0 0 | 3D Model (Arch) | 0 |  |  | 0%
[7 empty] | 5 2 0 | Arch GA's/Sects/Isoviews |  |  |  | 0%
2 2 0 | GA-PLAN (New) | 4 | 30 | 120 |  |  | 6 0 0 | Equipment Drawings to Vendor |  |  |  | 0%
2 2 0 | GA-PLAN (Existing) |  |  | 0 |  |  | 7 0 0 | Electrical Drawings | 1314 |  |  | 0%
2 2 0 | GA-SECT (New) | 4 | 10 | 40 |  |  | 8 0 0 | Standard Drawings |  |  |  | 0%
2 2 0 | GA-SECT (Existing) |  |  | 0 |  |  | 9 0 0 | BOM's | 60 |  |  | 0%
2 2 0 | GA-ISOVIEW (New) | 4 | 10 | 40 |  |  | 9 1 0 | Project Animation | 0 |  |  | 0%
2 2 0 | GA-ISOVIEW (Existing) |  |  | 0 |  |  | 9 2 0 | As-Building | 60 |  |  | 0%
[7 empty] | TOTAL DRAFTING HOURS: |  | 3100.024 |  |  | 0%
2 3 0 | ISOMETRICS (New) | 5 | 10 | 50 | # of lines/P&ID=6 X # of Iso/Line=2.5
2 3 0 | ISOMETRICS (Existing) |  | 0 | 0 |  |  |  |  | Make sure we include Paul Bond time here
2 5 0 | PRM's / ALIGN.SHTS |  | 0 | 0
3RD DELIVERABLES (SHOP FABRICATION PACKAGES)
2 2 0 | GA-FAB PKG PLAN |  | 0 | 0
2 2 0 | GA-FAB PKG SECT |  | 0 | 0
2 2 0 | GA-FAB PKG ISO |  | 0 | 0
2 3 0 | ISO-FAB PKG |  | 0 | 0 | # of lines/P&ID=6 X # of Iso/Line=2.5
EQUIPMENT DEVELOPMENT
6 0 0 | GA-BID DWG |  | 0 | 0
0 2 1 | EQUIP VENDOR CHK |  | 0 | 0
PIPING CHECKING
0 2 0 | CHECKING P&ID/Plot | 2 | 21 | 42 | 2hr/# of dwgs
0 2 1 | CHECKING GA's | 3 | 30 | 90 | 3hrs/# of dwgs
0 2 2 | CHECKING ISO'S | 1 | 10 | 10 | 1hr/# of Isometrics
SUPERVISION
0 0 1 | Piping Lead | 5% | 1518.48 | 75.924 | 5% of total hours
0 0 2 | Meetings | # of Wks | 50 | 100 | 2 Hours Once a week
0 0 2 | Hazop/Review/Client | 10 | 4 | 40 | 10 hrs / Meeting
MISC
9 0 0 | BOM | 2 | 30 | 60 | 2 hrs per GA
0 0 3 | FIELD TRIPS | 20 | 3 | 60
9 1 0 | PROJECT MOVIE |  | 0 | 0
9 2 0 | As-Building | 2 | 30 | 60 | 2hr/# of dwgs
TOTAL PIPING HOURS |  |  |  | 1481.924
BWBS | STRUCTURAL ESTIMATE
Code | DESCRIPTION | HRS/ | QTY | HRS |  | COMMENTS
MODELLING
3 0 0 | Structural Modeling |  | 0 | 0 | 4hrs/# of dwgs
4 0 0 | Civil Modeling |  | 0 | 0 | 4hrs/# of dwgs
5 0 0 | Arch Modeling |  | 0 | 0 | 4hrs/# of dwgs
1ST DELIVERABLES
3 2 0 | Struct Steel Dwg's | 6 | 10 | 60
4 2 0 | Civil Dwgs's | 6 | 5 | 30
2ND DELIVERABLES (SHOP FABRICATION PACKAGES)
3 2 0 | Pkg. Steel Dwgs's | 6 | 1 | 6
3 2 0 | Pkg. Steel Sect | 6 | 1 | 6
3RD DELIVERABLES
5 2 0 | Architectural Dwg's |  | 0 | 0
STRUCTURAL CHECKING
0 3 0 | Checking Struct | 3 | 10 | 30 | 3hrs/# of dwgs
0 4 0 | Checking Civil | 2 | 10 | 20 | 2hrs/# of dwgs
0 5 0 | Checking Arch | 1 | 5 | 5 | 1hrs/# of dwgs
SUPERVISION
0 0 1 | Structural Lead | 10% | 157 | 15.7 | 10% of Total Struct/Civil Hours
TOTAL STRUCTURAL HRS |  |  |  | 172.7
BWBS | ELECTRICAL ESTIMATE
Code | DESCRIPTION | HRS/ | QTY | HRS |  | COMMENTS
DELIVERABLES
7 0 0 | Preliminary Drawings | 6 | 10 | 60
7 0 0 | MCC Drawings | 6 | 3 | 18
7 0 0 | Area Clasification | 6 | 2 | 12
7 0 0 | Electrical single line | 6 | 1 | 6
7 0 0 | IRF Drawings | 6 | 40 | 240
7 0 0 | IFB Drawings | 6 | 40 | 240
7 0 0 | IFC Drawings | 6 | 40 | 240
7 0 0 | As Built | 6 | 10 | 60
0
CHECKING
7 0 0 |  | 3 | 146 | 438 | 3hrs/# of dwgs
SUPERVISION
0 0 1 | Electrical Lead | 10% | 1314 | 131.4 | 10% of Total Struct/Civil Hours
TOTAL ELCTRICAL HRS |  |  |  | 1445.4